## Sheet1
Sr.No. | B2BAssets Migration Status
| B2B Assets | Installation Status | Comments
1 | Advanced Product Search | DONE | UI Pending.
2 | Advanced Order Search | DONE | JS issues, UI Pending.
3 | Quickorder (UI Component) | DONE | JS issues, UI Pending.
4 | Quickorder (CSV Component) | DONE | UI Pending.
5 | Single view of order | DONE | UI Pending.
6 | Order Export Interface | DONE
7 | Customer Interface | DONE
8 | Product Interface | DONE
9 | Price Interface | DONE
10 | Stock Interface | DONE
11 | Product Restriction Interface | DONE
12 | Order Tracking Interface | DONE
13 | Multicarts | NOT DONE | Facing issues after multicarts installation.
14 | Image Resizing | NOT DONE | Issues related to media conversion
15 | Rsponsive Theme | PARTIALLY DONE | Storefront is already responsive, have to make changes for addons to make it responsive.
16 | UI Migration | NOT DONE | We required UI developer for UI migration, as we are facing lots of css/Js/Jquery issues.