## Sheet1
Sr.No. | B2BAssets Addons Migration 6.0
| B2B Assets | Efforts in hours | Comments
1 | hotfolder | 4
2 | interfaceerror | 4
3 | solrsearchrestriction | 9
4 | quickorder | 9
5 | productsearch | 9
6 | multicarts | 27
7 | singlevieworder | 18
8 | ordersearch | 18
Sr.No. | B2BAssets UI Migration 6.0
| Pages | Efforts in hours | Comments
1 | Home page | 20
2 | Login Page | 10
3 | Advanced Search Page | 20
4 | Product List Page | 20
5 | Product Details Page | 20
6 | Cart Page | 20
7 | Multi Step Checkout Summary Page | 40
8 | Order Confirmation Page | 20
9 | Profile Page | 25
10 | Update Password Page | 25
11 | Edit and Update Personal Details Page | 25
12 | Address Book Page | 25
13 | Add/Create new Address Page | 25
14 | Payment Details Page | 25
15 | My Quotes Page | 25
16 | Order History Page | 25
17 | Order Details Page | 25
18 | My Replenishment Orders Page | 25
19 | My Carts Page | 25
20 | Search Carts/Orders Page | 25
21 | Find a Store Page | 20
22 | Search Result Page | 20
23 | Manage Budgets Page | 25
24 | Create/Add new Budget Page | 25
25 | Manage Cost Centers Page | 25
26 | Create/Add new Cost Center Page | 25
27 | Manage Business Units Page | 25
28 | Create/Add new Business Unit Page | 25
29 | Manage Users Page | 25
30 | Create/Add new User Page | 25
31 | Manage Usergroups Page | 25
32 | Create/Add new User group Page | 25
33 | Manage Permissions | 25
34 | Create/Add new Permissions Page | 25
35 | Order Approval Dashboard Page | 25
36 | OrderForm Page | 20
Note: The UI estimation mentioned above is approximate. It might take longer time to complete.