## Sheet1
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
13-06-2016 | Today | Installing hotfolder, interfaceerror, solrsearchrestirction assets. Resolving issues. | Did B2BAssets AWS setup on local machine and started integration with Vivocha, Monitoring of B2BAsset, Klarets, Fashionistas, Pizzahut | Working on Migrating the interfaces of b2bassets from 5.7 to 6.0 | Created b2bassets store, Working on addons & Working on Pizzahut store for customer demo. | Working on comingsoon products and product addons in B2C | Working on B2B setup,oms and payment gateway integration | Set up B2BAssets on local machine for Migration activities. Started working on customization in Pizzahut store | IBM monitoring and solved issues related to that.And working on addons Registration. | IBM monitoring and solved issues related to that.
| Yesterday | Setup hybris 6.0 on local machine for b2bassets migration. Created b2bassets extension, made necessary changes. | Setup of hybris 6 | Setup Hybris v6.0 and up the default store | Extracted hybris v6.0 suit |  |  |  |  | IBM store was not running so started all the servers and solved issues regarding that.
| Hardship | No issues | faced issues with database | No issues | No issues | No issues |  | no issue | No issues
Need Help
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
14-06-2016 | Today | Installing quickorder, productsearch addons. Resolving issues. | Completed Integration of B2BAssets_AWS with Vivocha on local machine, Working on quickorder addon in migration of b2bassets from 5.7 to 6.0 | Monitoring of B2BAsset, Klarets, Fashionistas, Pizzahut & Working on cms content for quickorder addon. | Working on Pizzahut store for customer demo. | Working on Asianpaints customer demo | Working on B2C setup,oms and payment gateway integration. Addons,registration,etc | working on creating a new custom component in the pizzahut store | Working on Asianpaints customer demo | Setup of hybris 6 and IBM monitoring.
| Yesterday | Installed hotfolder, interfaceerror, solrsearchrestriction. Resolved assets related issues. | Did B2BAssets AWS setup on local machine and started integration with Vivocha | Working on Migrating the interfaces of b2bassets from 5.7 to 6.0 | Created b2bassets store, Working on addons & Working on Pizzahut store for customer demo. | Working on product addons and registration page in B2C | Working on B2B setup,oms and payment gateway integration | Set up B2BAssets on local machine for Migration activities. Started working on customization in Pizzahut store | Working on Asianpaints customer demo | IBM monitoring and solved issues related to that.
| Hardship | UI issues related to js. | None | No issues | No issues | No issues |  |  | No issues
Need Help
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
15-06-2016 | Today | Installing singlevieworder, ordersearch addon. Resolving issues. | Completed quickorder addon, working on productsearch addon |  | Working on Asian Paints store for customer demo. | Working on registration and account page in B2C addons |  | working on creating a new custom component in the pizzahut store | Working on Asianpaints customer B2C demo | Setup Hybris v6.0 and up the default store and IBM monitoring.
| Yesterday | quickorder, productsearch installation done. UI pending. | Completed Integration of B2BAssets_AWS with Vivocha on local machine, Working on quickorder addon in migration of b2bassets from 5.7 to 6.0 |  | Working on Pizzahut store for customer demo. | Working on Asianpaints customer demo |  | working on creating a new custom component in the pizzahut store | Working on Asianpaints customer B2C demo | Setup of hybris 6 and IBM monitoring.
| Hardship |  | None |  | No issues |  |  |  | no issues
Need Help
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
16-06-2016 | Today | Installing multicarts addon. Resolving pagination & other issues related to multicarts. | Completed quickorder addon and productsearch addon now working on single view orders and order search |  | Working on customer demo ppt and preparing for the demo | Working on customer demo ppt and preparing for the demo |  |  | Working on customer demo ppt preparing for demo | IBM monitoring and creating database in DB2
| Yesterday | singlevieworder, ordersearch addons installtion done. Pagination issue is pending | Completed quickorder addon, working on productsearch addon |  | Going through the flow of entire customization that I did. | Working on registration and account page in B2C addons |  |  | Working on customer demo preparing for demo | Setup Hybris v6.0 and up the default store and IBM monitoring.
| Hardship |  |  |  | No issues
Need Help
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
17-06-2016 | Today | On Leave | working on single view orders and order search |  | preparing for the demo | preparing for the demo |  |  | IBM monitoirng and preparing customer demo | IBM monitoirng and installed UNICA
| Yesterday | multicarts Installation & Resolving regarding issues. | Completed quickorder addon and productsearch addon now working on single view orders and order search |  | Working on customer demo ppt and preparing for the demo | Working on customer demo ppt and preparing for the demo |  |  | Working on customer demo ppt preparing for demo | IBM monitoring and creating database in DB2
| Hardship |  |  |  | No issues |  |  |  | No issues
Need Help
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
20-06-2016 | Today | On Leave | Monitoring of B2BAssets, Klarets, Fashionistas and working on order search |  | Working on customer demo ppt and preparing for the demo | Developed Asianpaints B2C store again |  |  | IBM monitoring and preparing for customer demo | IBM monitoring and sorted the excell sheet of reesumes
| Yesterday | On Leave | working on single view orders and order search |  | Working on customer demo ppt and preparing for the demo | preparing for the demo |  |  | IBM monitoirng and preparing customer demo | IBM monitoirng and installed UNICA
| Hardship |  |  |  | No issues
Need Help
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
21-06-2016 | Today | Resolving multicarts issue. | working on product search addon UI issue |  | Working on customer demo. | Developed Asianpaints B2B store again |  |  | IBM monitering demo done and preparing customer demo | IBM monitoring and was managing all the central repository files and binaries
| Yesterday | On Leave | Monitoring of B2BAssets, Klarets, Fashionistas and working on order search |  | Working on customer demo ppt and preparing for the demo | Developed Asianpaints B2C store again |  |  | IBM monitoring and preparing for customer demo | IBM monitoirng and installed UNICA
| Hardship |  |  |  | No issues
Need Help
Date | Name | Kinnari | Minal | Karan | Vamshi | Rohit | Sanket | Arnob | Vikas | Preeti
22-06-2016 | Today | Installed multicarts addon. Facing few UI & javascript related issues. | working on product search addon UI issue |  | Working on customer demo. | preparing for the customer demo |  |  |  | IBM monitoring and solving issues related to UNICA installation
| Yesterday | Resolving multicarts issue. | working on product search addon UI issue |  | Working on customer demo. | Developed Asianpaints B2B store again |  |  | IBM monitering demo done and preparing customer demo | IBM monitoring and was managing all the central repository files and binaries
| Hardship |  |  |  | No issues
Need Help